Plan of Operation Sample Table for One Activity – Provide a short narrative and a Table for each activity with the Objectives and Outcomes (use this format for the table)

| Direct Academic Services to ABC High School Students |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: 12th grade students will be able to demonstrate a greater understanding of the opportunities available for financial assistance for college attendance Projected Outcome: The project expects 95% of the 12th grade students to participate in a workplace readiness and youth employment program by the end of the school year. |  |  |  |  |  |  |
| Activity Description | Implementation Process | Activity Date | Expected Participants, Per Session | Evaluation Plan | Date (s) | Person (s) Responsible |
| Remedial Classes | - Hold information session for parents and students - Identify students who need remediation - Work with students to complete remediation courses. - Follow-up with students to compare PARCC assessment and school unit assessment scores | Fall 2019 Spring 2020 Summer 2020 | 40 (260 total) | 1. Monitor student progress on course exams, assignments, and compare to pre-test baseline score. 2. Student self-report on remedial class experience 3. Track students who complete remedial class during sessions and on PARCC assessments | Planning 10/2019 thru 12/2019, Ongoing Recruitment Registration 12/2019 thru 2/2020 Classes *6/2019 to 8/2019 and *9/2019 thru 10/2019 | 1. August Brown, project director 2. Aaron Jupiter, GEAR UP SCHOOL coordinator 3. June Stars, project evaluator |